## Backlog
# | As a/n | I want… | So that… | Notes | Status | Assigned to
1 | User | To be able to manually input Instructors | A course schedule can be created and modified |  | Open
2 | User | To be able to manually input Courses | A course schedule can be created and modified |  | Open
3 | User | To be able to manually input Rooms/Buildings | A course schedule can be created and modified |  | Open
4 | User | To be able to manually input instructor/course preferences/priorities | A course schedule can be created and modified |  | Open
5 | User | To be able to import all of my course/instructor/preference information with a comma delimited file | A course schedule can be created and modified with the quickest possible method |  | Open
6 | User | To see a course schedule automatically created | The scheduling process becomes quicker and easier |  | Open
7 | User | To see a list of conflicts or other situations where manual intervention may be required | Discretion can be used to set the schedule accordingly |  | Open
8 | User | To have minimum disruption of current scheduling procedures | The schedule can be created smoothly and accurately |  | Open
9 | User | To have an easy to use, intuitive GUI | To allow ease of use among multiple departments |  | Open
10 | User | To have the ability to produce comma/tab deliminited data files that can be read with Microsoft Excel | The outputs can be provided to the Dean for final approval of the schedule |  | Open
11 | Developer | To create an easy to use GUI interface | It satisfies the needs of the users and is easy to use |  | Open
12 | Developer | To develop an automatic course scheduling algorithm | It will speed the creation of department schedules |  | Open
13 | Developer | To parse an input .csv format file | All instructors, courses, and preferences can be loaded simultaniously rather than manually |  | Open
14 | Developer | To develop a .csv file output object | Users can output a Microsoft Excel readable file |  | Open
15 | Developer | To develop the ability to add instructors | The scheduling algorithm can use these objects as well as having the ability to manually add them |  | Open
16 | Developer | To develop the ability to add courses | The scheduling algorithm can use these objects as well as having the ability to manually add them |  | Open
17 | Developer | To develop the ability to add rooms/buildings | The scheduling algorithm can use these objects as well as having the ability to manually add them |  | Open
18 | User | To have a precompiled list of courses and teachers | The program can read the list and create a schedule |  | Open
19 | User | To print the course schedule | The schedule can be distributed to teachers or kept for reference |  | Open

## Options
Open
Closed
Manecke
Webb
Eccleston